## Slide 1: Session six: A Monitoring and Evaluation System for aid for trade projects
UNITED NATIONS
Economic and Social Commission for Western Asia (ESCWA)
Expert Group Meeting on Monitoring and Evaluation Systems for Implementing Aid for Trade Bankable Projects in the Arab Region
Hammamet, Tunisia, 12-13 December 2013
Ghazi Ben Ahmed

## Slide 2: 1. Objectives of the M&E System
The M&E system describes how the performance and quality will be continuously monitored and how the outcomes and impacts of the project.
More specifically, the over-all purpose of the M&E is the measurement and assessment of performance in order to effectively manage the outcomes and outputs known as development results.
Performance is defined as progress towards achievement of results.

## Slide 3: Objectives of the M&E System (Cont.)
Traditional M&E focuses on assessing inputs and implementation processes.
In this framework, the focus is on assessing the contributions of various factors to target development outcomes.
Likewise, this framework will provide management information needed for checking on the progress of support activities and to involve key stakeholders in learning to improve project implementation.
The M&E system will provide quantitative and qualitative performance data by which the achievements of the desired results can be measured and judged to inform the strategic planning process at critical points.

## Slide 4: Objectives of the M&E System (Cont.)
A careful analysis of the project design should be undertaken to determine:
1. the purpose and scope of the M&E system;
2. performance measures and the requirements of users of the M&E information;
3. the sources of information and gathering methods;
4. the responsibilities for M&E;
5. critical reflection processes and events;
6. how M&E information is to be reported and used and capacity building.

## Slide 5: 2.Features of an M&E framework
An M&E framework provides the following basis for monitoring:
1. the attainment of defined target results through outcome monitoring;
2. the information needs at different levels of the management structure;
3. methods to assess project progress and performance against work plans;
4. resource schedules and budgets;
5. the quality of key project activities and outputs;
6. responsibilities for undertaking monitoring activities at all levels;
7. formats for reporting progress and achievement and issues/problems and remedial actions.

## Slide 6: 2.Features of an M&E framework (Cont.)
Similarly, the M&E framework should provide the following basis for evaluation:
1. systematic collection,
2. analysis and assessment of potential project impacts and associated indicators through outcome evaluation;
3. identification of key stakeholders impacted by the project;
4. critical questions to explore - based on hypotheses, assumptions and major risks inherent in the design;
5. summary descriptions of key tools and methods to be used for evaluation;
6. responsibilities for undertaking evaluation activities and associated reporting and implementation plan for evaluation activities.

## Slide 7: 3. The composition of an M&E system
Ideally, a Monitoring and Evaluation System of any development intervention should have at a minimum, six elements
1. Clear purpose and scope;
2. Indicators and information needs;
3. Plan for information gathering and analysis;
4. Plan for reporting and communication;
5. Plan for critical reflection processes and events; and
6. Existence of the plan for necessary conditions and capacities.

## Slide 8: 1. Clear purpose and scope
Purpose: to support the project management to ensure compliance with the project’s strategy and approach, to improve responsiveness, efficiency and effectiveness by providing constant feedback from the beneficiaries, project staff and other stakeholders, and to contribute to the learning of all stakeholders by promoting policy dialogue.
Scope. The scope is concerned with the extent and level of sophistication of the M&E system. M&E systems can be highly sophisticated, requiring high levels of expertise in qualitative and quantitative research methods and extensive information management. Conversely, M&E systems can be simple, requiring minimal gathering of data and largely depending on discussions with stakeholders.
The appropriate level of sophistication of an M&E system will be determined by primarily the following four issues: (i) the M&E purpose, (ii) the available resources, (iii) available M&E expertise (including among primary stakeholders and partner organizations, and (iv) desirable level of participation in M&E by primary stakeholders and partner organizations

## Slide 9: 2. Indicators and information needs
Indicators help communicate changes that are usually more complex. Indicators help reduce data to be symbolic representation of a project objective, in a manner relevant and significant for those who will use the information.
Information needs are identified through understanding information needs of various stakeholders. Each level of the objective hierarchy (i.e. from bottom up: activities, outputs, outcomes and impacts) needs to have its on information requirements.

## Slide 10: 3. Plan for information gathering and analysis
An assessment of what information can be realistically collected, given available human and financial resources;
For each information need for indicator, there should be an elaboration of the ways information will be collected and organized;
Details of who to use what information and which method to gather/synthesize what information;
Schedule of frequency of information collection, when, place of collection, persons to be involved, expected information product;
Existence of technical and resource feasibility of information needs, indicators and methods;
Existence of formats for data collection and synthesis.

## Slide 11: 4. Plan for reporting and communication
Existence of a list of all the key audiences, their information requirement, when they need it and the format they need the information in.
Existence of a comprehensive schedule for information production, showing who will do what and by when.
Definition of what is to be done with the information (whether simply for onward transmission, for analytical discussion, etc.).

## Slide 12: 5. Plan for critical refection processes and events
Existence of detailed methods/approaches to use, with which stakeholder groups and for what purpose.
Identification of who is responsible for which reflective events.
Existence of a schedule for integrating all the key lessons and recommendations and a monitoring system of progress to that effect.

## Slide 13: 6. Existence of plan for necessary conditions and capacities
Number of M&E staff
Their responsibilities and linkages
Organizational relationships between key M&E stakeholders
Incentives needed to make M&E work
The type of information management systems to be established and a detailed budget

## Slide 14
Example: the DFID process for agreeing and providing support under Aid for Trade

## Slide 15: DFID’s Value for Money and Results Process
Notes: BUSINESS CASES
 Embeds evidence and consideration of value for money early in the decision making and design stages of all projects and programmes;
 Multilateral business case sets out the reforms and results we want to see to improve value for money from core financing;
 Strengthens DFID’s commercial awareness to ensure intervention design yields better value for money in procurement;
 Clarifies our approach to evaluation from the outset and in the design of the intervention; and
 The quality of appraisal and the Business Case more generally is assured through the Quality Assurance Unit and Chief Economist.
The Business Case is mandatory for all new funding proposals. The Business Case sets out the rationale for choosing an intervention. It provides a consistent approach to choosing from design and/or delivery options for an intervention, and for setting out the need. Theory of change thinking should initiate and drive the Business Case process and rationale for DFID intervention.
Assessment of evidence plays a critical role in four parts of the Business Case: in the Strategic Case – justifying the need for the intervention; in the Appraisal Case – demonstrating why we think the intervention will work; in the financial case – when determining budget for the intervention and assessing affordability; and in the Management Case – understanding how well the intervention is working and priorities for evaluation. Strengthening the use of evidence in decision making is one of the key aims of the Business Case.
The Results Chain explicitly sets out the results to be achieved by the intervention and will be informed by evidence of what works and the team’s thinking about the theory of change for the intervention.
Business Case
1. Strategic Case – sets out the context, the need, and rationale for DFID intervention. It also sets out the Impact and Outcome expected from the intervention;
2. Appraisal Case – explores how DFID will address the need set out in the Strategic Case, appraises options, and identifies which best delivers value for money;
3. Commercial Case – ensures that the delivery route for the preferred option is commercially viable and delivers value for money;
4. Financial Case – establishes that the preferred option is affordable and that the principles of sound financial management for public funds are followed;
5. Management Case – sets in place the governance arrangements necessary for the successful delivery of the intervention including procedures for monitoring and evaluation.

## Slide 16: DFID Evaluation Policy
The UK government has made results, value for money and evaluation central to its approach to tackling poverty and promoting growth.
DFID has been transforming its business processes to ensure evaluation considerations are embedded at all stages of the policy and programme cycle.
This is an ambitious approach which includes promoting change and building capacity of partners, as well as within DFID.

## Slide 17: DFID Evaluation Policy (Cont.)
DFID follows the OECD DAC international quality standards for evaluation:
“systematic and objective assessment of an on-going or completed project, programme or policy, its design, implementation and results in relation to specified evaluation criteria”.
DFID evaluations are guided by the core principles of: Independence, transparency, quality, utility, ethics.
DFID Evaluation Requirements and Standards:
Clear identification of need and justification for what is to be evaluated and why.
Consideration of any relevant systematic reviews of available evidence.
A significant and appropriate level of resource is allocated specifically to evaluation.
Designed to meet the information and decision-making needs of the intended users.
Use of 5 OECD DAC criteria.
Theory-based and impact approaches
Mandatory quality assurance requirements
For an evaluation to be classified as such, it must fulfil the 3 conditions of independence, transparency and robust methodology.
Relevance – extent to which objectives of a development initiative are consistent with the needs of those it intends to benefit.
Effectiveness – extent to which the planned results were achieved, or are expected to be achieved.
Efficiency – measure of how economically resources/inputs (funds/expertise/time) are converted into results.
Sustainability – actual or probable continuation of benefits from an inititative after major development assistance has been completed.
Impact – positive and negative, primary and secondary effects, direct/indirect, intended/unintended.
Recognition that not all criteria applied in every case, although each study should define which criteria were chosen and why, as well as the methods used to gather and analyse the data.
Mandatory for all evaluations to be independently QA’d during the design phase (entry) and at the draft final report (exit) stage.

## Slide 18: Case Studies: DFID M&E Frameworks
The Trade Advocacy Fund (TAF) offers short-term support to the poorest developing countries to help them to engage in crucial trade negotiations.
The TAF evaluation framework assesses the programme at three levels:
Level 1, Processes: An assessment of the processes designed for TAF, and their implementation by the Fund Manager and where relevant the involvement of DFID;
Level 2, Projects: An assessment of a range of individual projects funded by TAF to follow through from initial contact and tracing the theory of change as far as possible;
Level 3, Programme: An aggregate assessment of programme performance based on scoring of individual projects.

## Slide 19: Case Studies: DFID M&E Frameworks
The TAF evaluation strategy is to assess whether the Trade Advocacy Fund TAF design and operations adequately addresses the problem it was intended to overcome. DFID approach builds on the foundations of monitoring arrangements which will be carried out by the Trust Fund Manager (FM), to assess whether the programme is carrying out the activities described and developed in the programme design process.
It will also trace the links between the outputs of the TAF to the anticipated effects on trade negotiations.
TAF uses the OECD DAC criteria for evaluation as the central organising framework for this. However, recognising the importance of a strong focus on the value for money aspects of the evaluation, TAF further added economy as a criterion.
Notes: LEVEL 1: Processes
An annual quality assurance of FM implementation procedures.
Initial light touch review of procedures – focussed on the extent to which procedures will support evaluation, and are consistent with the TORs –carried out during the inception phase.
A light touch review of management information and monitoring arrangements.
LEVEL 2: Projects
This includes an annual quality assurance of the Fund Manager implementation procedures.
The initial light touch review of procedures – focussed on the extent to which procedures will support evaluation.
A light touch review of management information and monitoring arrangements will took place in June 2012.
LEVEL 3: Programme
The third component of the TAF evaluation aims to add a quantitative dimension by assessing the estimated approximate costs and benefits of the various interventions (i.e. the portfolio average rate of return) and then by the ex post recalculation of the benefit cost ratio

## Slide 20: TAF Results Framework

## Slide 22
The German Cooperation

## Slide 23: Division of labour among implementing agencies
GIZ (technical cooperation) largest German implementing agency with regard to TRA with about 1/3 of total German TRA volume.
KfW (financial cooperation) largest implementing agency with regard to AfT with about 50% of total German AfT volume (mainly category 3).
In total, considerable fluctuations of total AfT volume due to changing reporting practices used by one agency (DEG, a KfW subsidiary).
PTB (German national metrology institute) as main institution with regard to Quality Infrastructure

## Slide 24: Specific features in German AfT
Trade as crosscutting issue extending over wide range of themes, not as specific sector.
AfT disbursements largely bilateral, in the context of following priority areas: Sustainable Economic Development, Environment and Resource Protection, Governance and Civil Society, Food Security and Agriculture, Energy and Transport and Communication.
Multi-level approach: national/gov, meso, micro.
Target groups: whole population, focus on integration of women and poor and vulnerable groups.

## Slide 25: Case Study
Establishing a regional Quality Infrastructure in the East African Community (PTB, AfT category 1, code 33130; 2004-2013, €4.3 million).
Summary: establishment of legal framework for regional Quality Infrastructure and internationally recognized accreditations system, development and harmonization of standards.
Lessons learnt: despite regional context, national industrial interests of high importance (EAC has no sanction mechanism towards countries opposing regional integration attempts).
Success Factors: due to its independence, expertise and neutrality, PTB was accepted by all stakeholders.
Results: private sector increasingly uses QI services, border procedures have been streamlined within EAC and intra-regional trade has increased.

## Slide 26: Evaluation issues
Clarification of the evaluation object (e.g. ‘hard’ vs. ‘soft’ infrastructure; what has trade relevance but is not listed in CRS? What is listed but has no clear trade focus?)
Trade Marker: internationally agreed approach for allocation?
Evaluation method: Econometric approaches show methodological limitations, lack of consistency in main findings (e.g. which reductions in trade costs have largest impact?); quasi-experimental methods second-best alternative (see e.g. Volpe 2011, Brenton/von Uexkull 2009); RCTs problematic due to rare situations of ‘clinical’ interventions, baseline data, incentives and costs (Cadot/De Melo, 2013)

## Slide 27: Further Points of Discussion
Prism of Evaluation Approaches (Cadot/Newfarmer, 2011): 1.aggregate cross-country 2.sectoral/programme-level 3.project-level.
Reconstruction of Theory of Change will be central for Deval, but….:
‘Most AfT evaluations say little about trade’ (ODI, 2013): what about project designs then? And what about the usefulness of synthetic reviews or meta-evaluations, when primary evaluations have little about trade ?
Intersection with e.g. PSD and regional integration programmes: how can synergies between different evaluations be exploited.