## Slide 1
Expert Group Meeting on Monitoring and Evaluation Systems for Implementing Aid for Trade Bankable Projects in the Arab Regioin
The Enhanced Integrated Framework (EIF) at WTO
James Edwin, EIF Executive Secretariat
Jinene Hammamet, Tunisia 12-13 December, 2013

## Slide 2: Presentation Sequencing
EIF/WTO and its Governance Structure
What is an eligible Bankable AfT project for EIF funding?
The EIF Tier 2 project cycle
Role of M&E in EIF Project
LDC match to join the global trading system

## Slide 3: What is the EIF and its Governance Structure

## Slide 4: What is the EIF and its Governance Structure
The EIF is an Aid for Trade (AfT) partnership which support Least Developed Countries (LDCs) to be more active players in the global trading system
The global partnership includes 49 LDCs, 23 donors and 6 Core Agencies, 1 Observer Agency, the EIF Executive Secretariat (ES), the EIF Trust Fund Manager (TFM) and other development partners

## Slide 5: The EIF and its Governance Structure
Global Level
  EIF Steering Committee
  EIF Board
  ES and TFM
Country Level
  EIF National Steering Committee
  TAC 1&2
  Focal Point/NIU
  Donor Facilitator
  ES and TFM

## Slide 6: What is the EIF and its Governance Structure
The EIF aims at creating a strong and effective results -oriented partnership to trade through:
  Mainstreaming trade into national development strategies;
  Setting up structures needed to coordinate the delivery of Trade-related Technical Assistance (TRTA);
  Build capacity to trade, which also includes addressing critical supply-side constraints.

## Slide 7: What type of Aid for Trade support does EIF provide? &
EIF Bankable Project

## Slide 8: What is an EIF/WTO bankable Project
EIF uses two windows to fund projects: Tier 1 and Tier 2
Tier 1
Tier 2
Bankable project is a Tier 2 project which is aimed at assisting in the implementation of priority projects identified in the DTIS Action Matrix.

## Slide 9: What is an EIF/WTO Bankable Project
These priority projects should be:
  strategically selected to complement existing projects or fill gaps;
  Also where appropriate, small, low-cost and strategic projects are consolidated into a broader Tier 2 project.

## Slide 10: Types of Tier 2 projects
Trade policy and regulation
(e.g. helping countries to develop trade strategies, WTO accession, implement WTO commitments, and trade mainstreaming activities, build ministry capacity to implement trade strategies)
Trade-related infrastructure.
  (e.g. small roads, ports to connect domestic markets to the global economy, customs, standards and quality infrastructure)
Building productive capacity
(e.g. supporting the to private sector/small businesses to exploit their comparative advantages and diversify their products, tourism)
Trade-related adjustment
  (Non at the moment)

## Slide 11: Types of Tier 2 projects cont……
Small infrastructure projects may also be considered by the EIF Board on a case-by-case basis
if they are of a limited and focused scope;
if they address a supply-side constraint that has been identified in the DTIS Action Matrix; and
if they are part of the implementation of the midterm programme.

## Slide 12: Funding of Tier 2 Projects
Funding comes from a multi donor trust fund (EIFTF);
The bulk will need to come from programmes funded by bilateral or multilateral Development Partners (DPs);
While cost-sharing with EIF Country governments is encouraged, modalities for co-funding by other donors are yet in the works.

## Slide 13
What is the process for an EIF Bankable Tier 2 Project ?

## Slide 14: Process for a Tier 2 Project For EIFTF
Project must come from DTIS Action Matrix;
Project prioritised through consultation between all country level stakeholders;
Project must be approved by the EIF National Steering committee;

## Slide 15: Process for a Tier 2 Project For EIFTF
The Focal Point supported by the Donor Facilitator needs to have ensured that the proposed project does not duplicate any projects in the pipeline of any bilateral or multilateral donors;
The project should have true country ownership.

## Slide 16: EIF Value for Money Bankable Project Development Process
Submit final project proposal to EIF Board for approval
Finalise project proposal with guidance
from technical experts and ES /TFM
Share draft proposal document with
EIF ES and TFM
Expand the logframe into a full project
proposal
Develop the logframe: the project
‘backbone‟

## Slide 17
What is the role of M&E in EIF supported Projects?

## Slide 18
Output
Impact
Outcome
Input
Process/
Activities
Planning
Influenced by Management
External forces
<number>
Effective M&E leads to an efficient Results-based management system (RBM);
In project management, RBM is a management strategy focusing on performance and achievement of results.
Performance monitoring
Implementation monitoring
M&E in the Results Chain

## Slide 19: Monitoring at all stages of the project cycle
Programming/Planning
Implementation
Formulation
Evaluation
Identification
Appraisal
Financing
Notes: <number>

## Slide 20
Outcome
Outputs
Activities
Inputs
Impact
Funds for road construction, equipment staff provided
Construction and repair of roads occurs
300 km of road is completed and/ or repaired
‘Want to see’
More products are sold because of access to market; journey time reduced.
‘Hope to see’
Trade activity improves , household income increased, economic development improved
Implementation
Results
(c) EIF 2011
Planning
Notes: 1.
<number>

## Slide 21: IDENTIFY Key Performance INDICATORS (KPI) Baselines, Milestones and Targets
One of the key strengths of the logframe approach is that it forces the planning team to build into the design how the project will be monitored and evaluated;
Indicators and verification are needed to show what data we intend to use to measure progress, and how that data will be collected
In most circumstances there is not enough baseline data available at the design stage against which progress can be measured; in which case the logframe helps to pinpoint the gaps and determine what needs to be done.
Notes: <number>

## Slide 22: How do we focus M&E in RBM
<number>

## Slide 23
What is the Evaluation Component of the EIF

## Slide 24
Levels of Evaluation
3 levels of evaluation for the EIF:
Mid-term review (useful to consider revision of objectives)
End of project or final evaluation (to assess the achievement of the project purpose)
Ex-post or impact evaluation (to assess sustained benefits and overall impact)
Optional
Ex Ante- Feasibility Studies
Notes: <number>
<number>

## Slide 25: EVALUATION
Assesses the relevance, efficiency, effectiveness, impact and sustainability of projects in relation to stated objectives;
It links results-to-purpose and purpose-to-overall objectives of the project/program;
It is based on the guiding principles of impartiality, independence and credibility.
Ways to evaluate inputs, activities, outputs outcomes and impacts are essential components of M&E.
Notes: <number>

## Slide 26: Results Chain
Inputs
Activities
Outputs
Outcomes
Impact (Goal)
Effectiveness
Programme / Ministry level
STRATEGY
Efficiency
Project / department level
WORK PLAN
National Level
Indicators
immediate
6months – 1 year After implementation
immediate
5 years or more
2 to 5 years
Project / Department
Level Indicators
Notes: <number>

## Slide 27: Designing Good Evaluations
“Better to have an approximate answer to the right question, than an exact answer to the wrong question.” Paraphrased from statistician John W. Tukey
Getting the questions right is critical
Answering the questions is critical
Supporting public sector decision-making with credible and useful information is critical

## Slide 28: This Concludes the Presentation
EIF Executive Secretariat at the WTO:
email: eif.secretariat@wto.org
Web: www.enhancedif.org
Notes: <number>

## Slide 29: Planning a Monitoring System
Purpose:
Serve as the basis for establishing the project’s information systems
Generate information that will allow project managers to:
  track achievement of project outputs (immediate results of project activities) , and
  monitor progress towards achievement of objectives and desired outcomes (interim results created by outputs)
<number>
Notes: <number>

## Slide 30: Planning a Monitoring System
What should be monitored?
  Keep information requirements to a bare minimum
  Collect info that will be most helpful to those who will use it
How?
  Select methods to track indicators/report on progress
    Observations, interviews, routine reporting, sentinel sites
    Piggyback on existing data collection systems
    Both formal/informal and quantitative/qualitative methods
    Decide how information will be recorded systematically and reported clearly (use software e.g. excel, access, MS project, Prince 2, other specialized software)
    Consider the time and skills of those who will collect the data
    Pretest new monitoring instruments
<number>
Notes: <number>

## Slide 31: Planning a Monitoring System
Who should be involved when?
  Clearly identifying who will collect information on indicators, when (frequency) and who will receive it
  The monitoring plan should also identify who will be involved in reviewing progress and providing feedback
What resources are needed and available?
  The human and financial cost of gathering, reporting and reviewing data should be identified
  Needed funding and time should be set aside for this work
<number>
Notes: <number>

## Slide 32: Planning a Monitoring System
Consultation and Training
  Discuss the monitoring program with a representative group from each level before it is put into effect
  Provide training to those who will be using the monitoring systems
Using your M&E Framework Prepare a workplan
  for each year
  listing the main activities to be carried out, their output, timing and parties involved
<number>
Notes: <number>

## Slide 33: LEVELS OF INDICATORS
Impact-Level – indicators that show to what extent the project has contributed to achievement of its goals
Outcome-Level– indicators that show to what extent planned results at output and outcome or purpose level have been achieved
Ouput Level – indicators that show whether activities planned have been carried out and how. Also, used as measure of outputs
Activities – indicators that show what activities have been completed
Input Indicators – indicators that show what resources have been used by the project

## Slide 34: EIF outcomes (Results) and measurable indicators (NIU)
RESULT LEVEL | RESULT STATEMENT | INDICATORS
Goal | LDCs‘ integration into the global trading system with a view to contributing to poverty reduction and sustainable development | G1: LDC Members of WTO who have completed the accession process. G2: Per cent share of international non-oil trade from LDCs. G3: Poverty head count. G4: Per capita growth rate G5: Gini-coefficient
Purpose | To enable EIF Countries to become fully integrated and active players in, and beneficiaries of, the global trading system through mainstreaming trade. | P1: Value of non-oil goods traded P2: Non-oil goods trade diversification. P3: Logistics performance Index (LPI). P4: World Bank Doing Business – trading across borders. P5: Employment in non-traditional export sectors. P6: SMEs registered for import and export trade.
Outcomes | EIF Countries mainstream trade into their national development strategies and plans | O1.1: Tier 1 ‘Support to NIAs‘ project completed or under implementation in EIF Countries. O1.2: Number (and per cent) of active EIF Countries with complete, up-to-date (less than three years old) validated DTIS Action Matrices. O1.3: Level of capacity of the NIU to perform fiduciary programme management function for Tier 1 ‘Support to NIAs‘ project. O1.4: Number of EIF Countries with up-to-date (not older than five years) trade strategies. O1.5: Number of EIF Countries with quality trade strategies. O1.6: Number of EIF Countries with quality trade strategy implemented. O1.7: Number of EIF-funded projects achieving the expected results.
 | Coordinated delivery of trade-related resources (funding, technical assistance, etc.) by donors and implementing agencies to implement country priorities following the adoption of the DTIS Action Matrix | O2.1: Trade in PRSP and/or national development strategies O2.2: Existence of productive sector strategies for key sectors, integrating the trade dimension. O2.3: Functioning public/private consultation mechanism.
 | EIF Countries secure resources in support of initiatives that address DTIS Action Matrix priorities | O3.1: Availability of an annual rolling implementation overview integrating all trade-related government and donor-supported activities (where applicable, identifying activities specifically addressing gender and the environment). O3.2: Frequency of government and donor consultations on trade-related matters. O3.3: UN CEB Cluster activities are based on DTIS Action Matrix priorities in EIF Countries. O3.4: Number of countries with joint donor initiatives in the trade area (such as needs assessments; strategy formulations; programming; pooled funding; M&E; etc.).
 | Sufficient institutional and management capacity is built in EIF Countries to formulate and implement trade-related strategies and implementation plans | O4.1: Number of EIF Countries with implementation plan integrating DTIS/Action Matrix priorities and indicating financing needs to be met through ODA. O4.2: Number of EIF Countries where a government budget exists for the implementation of its trade strategy. O4.3: AfT flows to EIF Countries. O4.4: Number and amount of projects funded by donors related to the DTIS Action Matrix.
[1] Note how these outcomes correspond with the principles of the Paris Declaration and how the programme works to strengthen LDCs’ capacity to take ownership of and provide leadership around trade and development support related to Trade.
Notes: <number>

## Slide 35: Example M&E Framework
 | Indicators | Define Indicator | Baseline | Target | Sources of Verification | Assumptions
Goal/ Impact |  |  |  |  |  | 
Outcome |  |  |  |  |  | 
Output |  |  |  |  |  | 

## Slide 36: Example M&E Plan
Indicators (Definition % unit) | Base Line & Target Values (/Year) BL Y1 Y2 YN Target |  |  |  |  | Data Collection & Reporting |  | 
 |  |  |  |  |  | Frequency/Schedule | Instrument (Method) | Responsible Party
 |  |  |  |  |  | Annually (June) | Routine administrative records | Ministry of Trade
10
Example of a M&E plan for one indicator

## Slide 37
The Annual Work Plan
Year_______ Project Title______________________
Implementing Agency ________________
EXPECTED OUTPUTS AND INDICATORS INCLUDING ANNUAL TARGETS
PLANNED ACTIVITIES
List all the activities including monitoring and evaluation activities to be undertaken during the year towards stated outputs
EXPENDITURES
List actual expenditures against activities completed
RESULTS OF ACTIVITIES
For each activity, state the extent of delivery
PROGRESS TOWARDS ACHIEVING Results
Using data on annual indicator targets, state progress towards achieving the outputs. Where relevant, comment on factors that facilitated and/or constrained achievement of results
OUTPUT 1:
INDICATOR 1.1 WITH TARGET FOR THE YEAR:
INDICATOR 1.2 WITH TARGET FOR THE YEAR:
INDICATOR 1.3 WITH TARGET FOR THE YEAR:
OUTPUT 2:
INDICATOR 2.1WITH
TARGET FOR THE YEAR:
ETC.
Notes: <number>