## Slide 1: Session Four: M&E System for AfT bankable projects
UNITED NATIONS
Economic and Social Commission for Western Asia (ESCWA)
Expert Group Meeting on Monitoring and Evaluation Systems for Implementing Aid for Trade Bankable Projects in the Arab Region
Hammamet, Tunisia, 12-13 December 2013
Ghazi Ben Ahmed

## Slide 2: Purpose of the session
To work through and understand what we mean by intervention logic, theory of change and logframes….
….and how these link together
…working through theoretical examples and practical ones

## Slide 3: Intervention logic (or results chain)
Activity:
Building a one stop border post
Outcome 3: Reduction in trade costs
Outcome 1:
Reduction in time to cross borders
Outcome 2:
Reduction in transport costs
Output:
Number of one stop border posts built with hard and soft infrastructure operational
Impact: Increased trade

## Slide 4
Activity:
Building a one stop border post
Outcome 3: Reduction in trade costs
Outcome 1:
Reduction in time to cross borders
Outcome 2:
Reduction in transport costs
Output:
Number of one stop border posts built with hard and soft infrastructure operational
Impact: Increased trade
Intervention logic and theory of change
The logic behind logframes, although not always articulated
Theory(s): explain the causality
Assumptions: underlying the functioning of the theory
Theory(s): explain the causality
Assumptions: underlying the functioning of the theory
Theory(s): explain the causality
Assumptions: underlying the functioning of the theory
Theory(s): explain the causality
Assumptions: underlying the functioning of the theory
Theory(s): explain the causality
Assumptions: underlying the functioning of the theory

## Slide 5: Theory of change – why?
It is a structured technique for understanding how a project/programme is likely to contribute to long-term outcomes and impacts (the “how” and “why”)
It makes explicit the theory and assumptions behind the intervention logic or results chain – from activities to outputs to outcomes to impact
It allows for creative and dynamic thinking about how to achieve impact/goals
It generates a shared understanding of what is most important and achievable - the critical path
It guides “how” and “why” a complex change process will unfold (change can be complicated and messy... not straightforward… requires in-depth understanding)

## Slide 6: Theory of change – what? [DFID]
“Needs to include an explanation of how the programme’s activities contribute to the results – not simply a list of activities followed by the results, with no explanation of how these are linked, apart from a mysterious arrow”
“It is the process through which it is expected that inputs will be converted to expected outputs, outcomes and impact”
“Articulate the theories and assumptions which underpin the anticipated change process”
It is a construct based on our world view…. And it should be tested, revisited and revised.

## Slide 7: Theory of change – simple yet complex!
Theory of change needs to combine:
Presentational simplicity to quickly communicate the theory to all audiences, and…
Detailed information that does justice to the complexity of your programme, and explores the assumptions and evidence underpinning it

## Slide 8: Theory of change
DFID suggests providing:
- A one line snapshot of your theory of change
- A simple diagram to give a visual summary of your theory of change
- Narrative text which gives more detail on each of the causal links (theory), the assumptions and evidence (or lack of it) for each causal link
 (combines simplicity and complexity)

## Slide 9: Logframe and Theory of Change
Logframes:
designed to simply convey the essence of a project – often attempts to describe a project in four steps (activities -> poverty reduction)
linear cause-and-effect approach to complexity – deliver X (which will therefore deliver Y and Z)
increasingly used mainly as a performance framework
but do not show why activities are expected to produce outcomes
Theory of Change:
designed to explain how change happens
it embraces complexity
it focuses on causality - requires articulation of why X leads to Y
it does not include indicators
requires critical thinking
Complements, not alternatives

## Slide 10: How to develop a Theory of Change
From DFID guidance:
Start by clearly defining the problem
Next step: identify the desired impact of the programme
Backwards mapping – what needs to happen in the medium-term before that impact can occur (i.e. outcomes)? (a narrative explanation can sit alongside proposed outcomes and outcome indicators that would go in the logframe)
Identify the steps before that: what outputs are needed to deliver the long-term outcomes?

## Slide 11: How to develop a Theory of Change
It can draw on a mix of:
Expected effects based on evidence from diagnostics, research, policy, programmes and projects, as well as logical analysis
Demonstrated effects from observations (first hand or reported) of projects/programes work and what they have delivered. Including stakeholder experience of what works or not.

## Slide 12
Theory(s): explain the causality
Assumptions: underlying the functioning of the theory
Theory(s): explain the causality
Assumptions: underlying the functioning of the theory
Theory(s): explain the causality
Assumptions: underlying the functioning of the theory
Theory(s): explain the causality
Assumptions: underlying the functioning of the theory
Theory(s): explain the causality
Assumptions: underlying the functioning of the theory
Activity:
Building a one stop border post
Outcome 3: Reduction in trade costs
Outcome 1:
Reduction in time to cross borders
Outcome 2:
Reduction in transport costs
Output:
Number of one stop border posts built with hard and soft infrastructure operational
Impact: Increased trade
Evidence
Evidence
Evidence
Evidence
What we do becomes what we want to achieve
Evidence

## Slide 13
Draft checklist (DFID)

## Slide 14: Common problems
Poor theory – wrong solution to the problem (or right solution to the wrong problem – ill-defined problem)
Poorly specified intended results
Unintended results/consequences ignored
Treating potential solutions as simple – situation more complicated
Assuming causality! (A leads to B leads to C)
Taking a ‘one size fits all’ approach – not tailored/adapted to suit local context/needs
Not dynamic – not building in the ability to be flexibility as understanding improves over time and situations change