## Slide 1: 4. Tendering & Procurement Techniques for PPPs in ICT
by
Ned White
Institute for Public-Private Partnerships
February 17 - 19, 2008

## Slide 2
Module 3:
Identifying,
Analyzing &
Structuring
ICT
Projects to be
Viable PPPs
Module 4:
Tendering &
Procuring
PPP Projects
in ICT
Module 5:
Negotiating
Contracts &
Financing
PPP
Projects
in ICT
Module 6:
Managing
PPP ICT
Contracts
&
Monitoring
Contractor
Performance
The Sequence of the Project
Life Cycle for
PPPs in ICT & e-Government
Module 2: Establishing Effective Policy, Legal, Institutional,
& Regulatory Frameworks for PPPs in ICT/e-Govt.

## Slide 3: Session Overview:
Purpose, Goal & Objectives of PPP ICT Procurement
PPP Procurement Options
Stages of Competitive Tendering
Lessons Learned & Good Practices
Case Example – Johannesburg, South Africa’s 5-year ICT Network PPP Procurement

## Slide 4: Goals of PPP Procurement
The process and the result of selecting a private PPP contractor should be:
Fair: All qualified and interested private bidders should have an equal opportunity to participate in the selection
Equitable: The outcome should offer equal treatment to affected groups & stakeholders
Transparent: The process should be publicly defendable and open to independent review
Competitive: Competition IS necessary in order to maximize Value for Money benefits. Without competition the overall benefits of PPP are severely challenged.
Cost Effective: Competitive tendering for large PPPs can take a long time (1.5+ years), significantly adding to its “transaction costs.” Selection of procurement techniques should carefully weigh the relative size of transactions costs against the projected Value for Money benefits.

## Slide 5: Is Competitive Tendering for PPP Necessary?
“Availability Payments” from Govt. to ICT PPPs are public funds and they tend to be large. Public Confidence in PPP is increased if selection of the private contractor is open, fair & competitive.
Value for Money is maximized through competition
According to analyses of over 2,500 PPP transactions, PPP contracts awarded through open competition are much less likely to be re-negotiated, to have unscheduled prices/tariffs increases, to enter into dispute, to be cancelled, or to impose new “implicit liabilities” on fiscus. (WB PPI Database & L. Gausch)
Competition requires both public & private sectors to thoroughly analyze risks, allocate risks, and prepare risk mitigation up-front. Without competition, too many risks are left to be dealt with later… (at the expense of public’s VFM)
Competitively-procured PPPs have shorter construction & installation periods
However, competition does impose costs of longer procurement periods and higher bid preparation costs on both public & private sectors

## Slide 6: PPP Procurement Frameworks must reduce transaction costs over time to be sustainable
1st
2nd
3rd
4th
5th
PPP
Transaction
Costs ($):
Preparation
Times,
Development
Costs,
Financing
Risk Premia
Opportunity
Costs, etc.
Sequence of PPP Transactions

## Slide 7: PPP Procurement Standardization:
Standardized Templates for PPP Feasibility Studies & Project Structuring Proposals (PSCs, RA-PSCs, VFMs, Risk Analyses & Allocations, etc.)
Standardized Pre-Qualification Documents (RFQs) & Shortlisting Procedures
Standardized Requests for Proposals (RFPs) & Bid Evaluation Procedures
Standardized PPP contracts:
  General, cross-sector standard PPP contract provisions
  Standardized sector contracts (hospitals, schools, roads, Office Space, public facilities, water, IT, etc.)
Standardized PPP Contract Management & Performance Monitoring structures

## Slide 8: PPP Procurement Options:
Larger PPP Projects:
  Open Competitive Tendering (among qualified, short-listed bidders)
Smaller PPP Projects:
  Competitive Negotiations
  Swiss Challenge: Allow others to beat the incumbent, unsolicited bid
  Direct Negotiations (“Sole Sourcing”)
  Unsolicited Proposals

## Slide 9: Step 1: Appoint the Govt. Project Procurement Team:
Headed by a Project Manager given full-time responsibility. Manager should have had substantial procurement experience
Team should also include technical, legal, financial and project management experts. Recently some teams have included consumer advocates to ensure that projects directly benefit end users
Project Team should have power to make decisions, to accept PPP feasibility study, to implement its recommendations, to select & hire PPP transaction advisors, and to approve final PPP contract awards.
Project Team Committee should have broad representation in the Government, and include some public members
Continuity: Members should serve thru final contract negotiations

## Slide 10: STEP 2: Implementing the Recommendations of PPP Feasibility Analyses & Proposed Structure
A traditional, technical feasibility study is not yet a complete, viable PPP Project. Other feasibility analyses must be completed (econ, enviro & social, financial, etc.) Plus the commercial viability (PPP) and risk analysis
The proposed PPP project risk structure must be complete (risk identification, allocation matrix, & mitigation)
Implement key recommendations before PPP is viable:
      Approval of Public Funding & Supports
      Acquisition of any Land needed (Donated or sold to Project Co.)
      Adjustments of End-use Tariffs
      Clarifications of Asset ownership, legal titles, use, etc.
      Completion of Ancillary infrastructure (connections, feeders)
      Permits, approvals & licenses
Retain experienced PPP Transaction Advisors
If necessary, revise Project Risk Structure prior to tendering

## Slide 11: PPP Transaction Advisors:
Experienced PPP Transaction Advisors help procurements proceed faster & better than without
Serious, experienced, & long-term private PPP ICT investors have more confidence in PPP tenders (fairness & transparency) supported by experienced transaction advisors, than without
UK, Australia, S. Africa, New Zealand and other Govts. with long experiences in PPPs (who could do all of this PPP tendering without outside advisors) still insist on using transaction advisors to best manage large “lumpy” PPP project caseloads and to ensure/incent successful closures.
PPP Transaction advisors usually have only there basic time & expenses “paid-as-they-go” but can only make their important bonuses or profits based upon success fees paid out at PPP financial closure
Costs of PPP transaction advisors can initially be met through a PPP Project Development Facility (PPP PDF). Serious private ICT investors are generally willing to pay some of these project preparation costs by buying RFQs and RFPs or by adding these project preparation costs to their own financial closing costs.

## Slide 12: Step 3: Preparing & Issuing Pre-Qualification Documents
Goals of PPP Pre-Qualifications:
For the Govt.: Generate maximum private interest in and competition for the project
To limit number of private firms (4-6) to submit detailed PPP bids:
  The smaller the number of actual bidders, the greater the chances a private firm could win, and the more it is willing to invest in preparing a better quality bid (rigorous, detailed due diligence)
  Govt. evaluators only need to evaluate 4-5 detailed, good quality bids rather than a mixture of 20 – 30 from serious bidders & “brief-case companies”
To ensure that actual private bidders have:
  Adequate, relevant ICT and sector experience (transport, public admin., etc.)
  Successful prior ICT & PPP experience with references
  Experienced personnel & equipment capabilities
  Financial capacity & any special Project Finance experience needed
  Ability to provide other priorities (affirmative action, etc.)

## Slide 13: Requests for Qualification (RFQs)
For the first Pilot PPPs, it is better to include more detailed information about the project in the RFQ package than less.
Let interested bidders know the Govt. is well-prepared and has invested a lot in analyzing & structuring the PPP project. Bidders must also be prepared invest a lot in their bid preparation as well
What to Include in the RFQ:
  Clear description of the goals & purpose of the project, expressed as discrete output standards & KPIs
  Summaries (or full copies) of feasibility analyses (tech, econ, enviro., social, etc.)
  Descriptions of proposed risk structure & risk allocation matrix
  Draft of PPP contract(s), if available

## Slide 14: What to include in a PPP RFQ:
Clear instructions to Interested Bidders to follow in submitting EoIs
Required Formats & Templates to follow for submissions:
  Organizational & legal structure of the consortium (how will it be owned & managed? Decisions made? Who will be in charge?)
  Listing & describing relevant technical capability (ICT sector project experience and PPP risk management experience)
  Financial capacity of consortium, including prior experience with PPPs & project-backed financing
  Personnel expected to work on project. Roles & CVs
  Experience with affirmative action & other Govt. priorities
Interested bidder’s comments on the proposed PPP risk structure of the project

## Slide 15: PPP Pre-Qual Evaluation Guidelines
General Experience:
  Years of experience in the sector
    Rule of thumb = 5 years or more
    Implications in a sector where there are few competitors
    How to define in case of consortia or joint ventures?
Particular Experience:
    Required number of similar “PPP” contracts completed
    Rule of thumb = Minimum of 2
    Should be within the last 5 to 20 years, depending upon length of contract being procured
Remaining criteria should be project-specific, for example
    Experience meeting similar KPIs & output standards
    Rule of thumb = Should expect bidder to demonstrate experience at a level equaling 70% of what is expected under contract being procured

## Slide 16: PPP Prequal – Evaluation Guidelines
Financial Requirements:
  Required average annual turnover
    Rule of thumb = No less than 1.5 - 2 x average annual revenue generated by service to be operated (multiplier can be lowered for larger contracts)
    For larger contracts, will restrict the field of competitors
    How to define in case of consortia or joint ventures?
  Minimum required cash flow
    Rule of thumb = Cash flow operator would require during the number of months it takes operator’s invoice to be paid
    Should not be less than 6 months
  Audited balance sheets
    Rule of thumb = 5 years
    Can be reduced to 3 years for small projects
    May have to allow exceptions for bidders that are small firms or from countries where auditing is not standard

## Slide 17: PPP Pre-Qual – Evaluation Guidelines
Personnel Capabilities:
  Key management positions
    Require CVs for key personnel
    Rule of thumb = 5 years experience in a similar position
    Carefully define what constitutes relevant experience
Joint Ventures:
  Partner limitations
    Rule of thumb = Three to five
    Risk of default is greater with larger number of firms
Domestic Bidder & Affirmative Action Preferences:
  For PPP arrangements make sure domestic private sector is very strong and credible

## Slide 18: PPP Pre-Qual – Evaluation Guidelines
Bidders should be allowed 4 to 6 weeks to prepare pre-qualification applications
Require prequal data to be broken down by consortium member for evaluation purposes
Require power of attorney for lead firm
Require references for each qualifying project listed under particular and general experience and check references
Require statement of litigation history
Provide applicants with standard forms in which to present prequalification information

## Slide 19: Sample PPP Pre-Qualification Criteria
Experience in financing PPP/BOT or similar limited recourse projects
Financial strength (size & quality)
Preliminary conception of financing
Experience in implementing PPP/BOT type projects
Experience in construction, maintenance, and operation of PPPs in same sector
Experience in advanced electronic revenue collection & customer management systems
Individual qualifications of key team personnel
Organization and management structure of project company
Ability & willingness to ensure large local contractor participation
Ability to work cooperatively with a broad range of government agencies and the public

## Slide 20: Step 4: Developing PPP Bid Documents
Evaluate if adjustments should be made to project output standards & KPIs based upon Expressions of Interest (EoIs). Update Analyses:
  Affordability,
  RA-PSC &
  Expected VfM (PPP Reference)
Request for Proposals/Tenders (RFP/RFTs)
  Restate clear output levels & KPIs
  Include full copies of all project feasibility analyses
  Include full description of project risk structure, risk matrix and full draft of PPP contract(s)
  Let bidders know how bids will be evaluated (ie the discount rate on costs) but not the affordability limit.

## Slide 21: Managing Competitive PPP Bids
Bidder’s conference 21-45 Days after release of RFP
  Instructions to bidders & Templates
Invite bidders to submit clarification questions in writing
Share all questions and responses to all bidders, in writing
Depending on project need, conduct a site inspection/walk-through (along right-of-way)
Transaction advisors help ensure the process moves smoothly and delays & protestable events are minimized.

## Slide 22: PPP Bid Evaluation: Two Envelope Process
Minimum proposal qualification
Technical envelope evaluated first
  Technical clarifications requested
  Notification of qualification (pass/fail)
  Qualified technical proposals to next round (financial envelope)
  Formal presentation/interview?
  “Non Responsive” bidders’ financial envelopes are returned sealed and unopened.
Financial envelope opened in public
Lowest responsive bidder (on a common NPV basis) wins

## Slide 24: PPP Procurement Issues
In UK, average length of time from first official advertisement of project opportunities to financial close is 27 – 29 months. Slight reduction since 1992
In the UK, the length of procurement periods is cited by both public sector managers and private bidders as the most important constraint to PFIs.
UK’s PFI framework accepts that rigorous due diligence by both public and private sectors is the source of PFI’s ability to deliver VfM, and should not be reduced.
The level of analysis & preparation should not be reduced, but the costs can be through:
    Enforcing the new, Revised, Standardised PFI contract
    Developing sector specific guidelines for PFI contract for health, education & defence
    Systematic capacity-building on PFI procurement through “Partnerships UK” (PPP)

## Slide 25: ICT PPP Procurement Case Example: Johannesburg, South Africa’s 5-year ICT PPP Contract

## Slide 26: Greater Johannesburg Metropolitan Council (GJMC)’s New ICT Needs
In 1994 South Africa’s new democratic constitution called for the systematic amalgamation of local governments; forming single, unified local and municipal government structures out of what had previously been separate “white” cities and “black” townships.
In 1996 the Greater Johannesburg Metropolitan Council (GJMC) was created out of what had been 15 different local governments. A key to making the new GJMC structure work as an effective governmental structure was to unify and coordinate the management and flow of Govt. information systems (budgeting, planning, monitoring, engineering, etc.)
In 1999 the GJMC approached the newly established Municipal Infrastructure Investment Unit (MIIU) a PPP technical-support unit, to assist with evaluating and structuring possible PPP approaches to GJMC’s e-Government needs.
A GJMC project committee was established to oversee the project’s development. In 1999 the GJMC appointed as transaction advisors HSBC Simpson MacKenzie.

## Slide 27: The PPP Project Cycle in South Africa:

## Slide 29: GJMC’s ICT PPP Procurement
With R1.3 million ($180,000) in financial support from the MIIU’s Project Development Facility, the transaction advisors prepared a PPP feasibility study.
This was reviewed by the GJMC’s Project Committee, which decided to proceed to competitive tendering. In mid-2000 four short-listed firms submitted bids.
Negotiations between GJMC’s Project Committee and the preferred bidder, a consortium of IBM and Masana Technologies (Pty), took place from July to September, 2000.
The PPP contract was finally signed in December, 2000 committing the GJMC to pay an estimated R590 million ($84 million) over 5-years for the design, installation, and operation & maintenance of a new ICT network to link all public functions of the Metropolitan Government.

## Slide 30: Questions?

## Slide 31: The Institute for Public-Private Partnerships (IP3) Washington | Cairo | Jakarta | Dakar
Cairo
19 Ahmed El Shattoury Street
Dokki, Giza, Egypt
Washington
1010 Wisconsin Avenue, NW, Suite 250
Washington, DC 20007 USA
Tel: 1-202-466-8930 Fax: 1-202-466-8934
www.ip3.org
Jeff Wuorinen
Regional Representative, Middle East/North Africa
E-mail: jwuorinen@ip3.org
Tamer Shaltout
Program Manager, Egypt
E-mail: tshaltout@ip3.org